## F26 TeamA Project - Sprint Back
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Communication interface | https://github.com/COS420-F25/F26-Group-A/issues/25 | Done |  |  |  |  | ryanhallett |  |  |  |  | D1 | Deliverable 1 QC
Export Porduct Backlog | https://github.com/COS420-F25/F26-Group-A/issues/16 | Quality Checking |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC
Export Sprint Backlog | https://github.com/COS420-F25/F26-Group-A/issues/17 | Quality Checking |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC
Write 1-5 non-functional requirements | https://github.com/COS420-F25/F26-Group-A/issues/18 | Done |  |  |  |  | ryanhallett |  |  |  |  | D1 | Deliverable 1 QC
Create 7 functional requirements | https://github.com/COS420-F25/F26-Group-A/issues/23 | Quality Checking |  |  |  |  | ngkelvn |  |  |  |  | D1 | Deliverable 1 QC
Create 7 functional requirements | https://github.com/COS420-F25/F26-Group-A/issues/24 | Quality Checking |  |  |  |  | winslop11 |  |  |  |  | D1 | Deliverable 1 QC
Updated Project Description Document | https://github.com/COS420-F25/F26-Group-A/issues/29 | Quality Checking |  |  |  |  | Elorm-K |  |  |  |  | D1 | Deliverable 1 QC
Update the User story based on feeedback | https://github.com/COS420-F25/F26-Group-A/issues/27 | Quality Checking |  |  |  |  | Elorm-K |  |  |  |  | D1 | Deliverable 1 QC
Write about the Group matching algorithm feature | https://github.com/COS420-F25/F26-Group-A/issues/33 | Quality Checking |  |  |  |  | ngkelvn |  |  |  |  | D1 | Deliverable 1 QC
Update README | https://github.com/COS420-F25/F26-Group-A/issues/34 | Done |  |  |  |  | ryanhallett |  |  |  |  | D1 | Deliverable 1 QC
Deliverable 0 Revision: Prior Solution 1 | https://github.com/COS420-F25/F26-Group-A/issues/35 | Quality Checking |  |  |  |  | Apex-04 |  | Cyril A. | 2026-10-05 | 2026-10-06 | D1 | Deliverable 0: QC
Make Prior Solution 2 revisions | https://github.com/COS420-F25/F26-Group-A/issues/36 | Quality Checking |  |  |  |  | zen2504 |  |  |  | 2026-10-06 | D1 | Deliverable 0: QC
Create system features for Teachers POV | https://github.com/COS420-F25/F26-Group-A/issues/31 | Quality Checking |  |  |  |  | zen2504 |  |  |  |  | D1 | Deliverable 1 QC
Deliverable 0 Revision: Overview and Description | https://github.com/COS420-F25/F26-Group-A/issues/37 | Quality Checking | [9 empty] | D1 | Deliverable 1 QC
Create 7 functional requirements | https://github.com/COS420-F25/F26-Group-A/issues/20 | Quality Checking |  |  |  |  | zen2504 |  |  |  |  | D1 | Deliverable 1 QC
User interface | https://github.com/COS420-F25/F26-Group-A/issues/21 | Quality Checking |  |  |  |  | alexh5427 |  |  |  |  | D1 | Deliverable 1 QC
Writing 6-10 non-functional requirements. | https://github.com/COS420-F25/F26-Group-A/issues/19 | Quality Checking |  |  |  |  | alexh5427 |  |  |  |  | D1 | Deliverable 1 QC
Initialize Codebase | https://github.com/COS420-F25/F26-Group-A/issues/32 | Quality Checking |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC
System Feature | https://github.com/COS420-F25/F26-Group-A/issues/26 | Quality Checking |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC
Initialize Codebase | https://github.com/COS420-F25/F26-Group-A/pull/38 | Done |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC
Sprint Review | https://github.com/COS420-F25/F26-Group-A/issues/39 | Quality Checking |  |  |  |  | Apex-04 |  |  |  |  | D1 | Deliverable 1 QC