## F26 TeamA Project - Post Sprint
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Integrate all D2 docs, links, submission folder | https://github.com/COS420-F25/F26-Group-A/issues/58 | 30-60% done | High | Requirements | 2 |  | Elorm-K, winslop11 |  | Andrew B. | 2026-10-25 | 2026-10-26 | D2 | Deliverable 2 QC
UML Package Diagram | https://github.com/COS420-F25/F26-Group-A/issues/47 | Done | High | Requirements | 2 |  | Apex-04, ryanhallett |  | Ryan B. |  | 2026-10-22 | D2 | Deliverable 2 QC
Turn D1 comments from Greg and turn Brightspace feedback to tasks | https://github.com/COS420-F25/F26-Group-A/issues/43 | Quality Checking | High | Requirements | 3 | 1 | Elorm-K |  | Kelvin N. | 2026-10-19 | 2026-10-20 | D2 | Deliverable 1 Corrections
Revise product backlog, reply to D1 comments | https://github.com/COS420-F25/F26-Group-A/issues/45 | Quality Checking | High | Technical work | 1 |  | ngkelvn, winslop11 |  | Andrew B. |  | 2026-10-21 | D2 | Deliverable 1 Corrections
Update Readme with Explicit Download and Installation Instuctions | https://github.com/COS420-F25/F26-Group-A/issues/57 | Done | High | Requirements | 1 |  | ryanhallett |  | Andrew B. |  | 2026-10-22 | D2 | Deliverable 2 QC
Merge A2 diagrams | https://github.com/COS420-F25/F26-Group-A/issues/51 | Done | High | Requirements | 3 |  | ryanhallett |  | Cyril A. | 2026-10-20 | 2026-10-20 | D2 | Deliverable 2 Submission
2 Mockups, Improve D1 wireframes, place in SRS | https://github.com/COS420-F25/F26-Group-A/issues/49 | Done | High | Requirements | 2 |  | ryanhallett |  | Cyril A. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 2 QC
Set Up Firebase and Basic Login System | https://github.com/COS420-F25/F26-Group-A/issues/65 | Done | High | Technical work | 4 |  | Apex-04 |  | Ryan B. |  | 2026-10-24 | D2 | Deliverable 2 QC
Set Up Build Enviroment and Dependecies | https://github.com/COS420-F25/F26-Group-A/issues/54 | Done | High | Technical work | 2 | 1 | Apex-04 |  | Ryan B. | 2026-10-19 | 2026-10-21 | D2 | Deliverable 2 QC
Export Sprint Backlog 1 (Post-Kickoff) | https://github.com/COS420-F25/F26-Group-A/issues/44 | Done | High | Requirements | 1 |  | Apex-04 |  | Cyril A. | 2026-10-19 | 2026-10-20 | D2 | Deliverable 2 QC
Write Issue Process in Wiki | https://github.com/COS420-F25/F26-Group-A/issues/40 | Done | High | Knowledge acquisition | 2 | 2 | Apex-04 |  | Cyril A. | 2026-10-18 | 2026-10-19 | D2
Edit the feedback on the NFR from D1 | https://github.com/COS420-F25/F26-Group-A/issues/61 | Done | High | Requirements | 2 |  | ryanhallett |  | Kelvin N. | 2026-10-20 | 2026-10-23 | D2 | Deliverable 1 Corrections
Update the wireframes using already existing example | https://github.com/COS420-F25/F26-Group-A/issues/63 | Done | High | Requirements | 4 |  | alexh5427, Elorm-K, ryanhallett |  | Andrew B. | 2026-10-20 | 2026-10-23 | D2 | Deliverable 2 QC
Respond to feedback on functional requirements that need editing | https://github.com/COS420-F25/F26-Group-A/issues/62 | Done | Medium | Requirements | 1 |  | zen2504 |  | Ryan H. | 2026-10-20 | 2026-10-23 | D2
2 Mockups, Improve D1 wireframes, place in SRS | https://github.com/COS420-F25/F26-Group-A/issues/52 | Quality Checking | Medium | Requirements | 2 |  | alexh5427 |  | Zach B. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 2 QC
Respond to feedback on SRS doc | https://github.com/COS420-F25/F26-Group-A/issues/41 | Done | Medium |  |  |  | ryanhallett |  | Cyril A. | 2026-10-16 | 2026-10-18 | D2 | Deliverable 1 QC
Export Sprint Backlog 2 | https://github.com/COS420-F25/F26-Group-A/issues/60 | In Progress | Low | Technical work | 1 |  | Apex-04 |  | Cyril A. |  | 2026-10-25 | D2 | Deliverable 2 QC
Write SRS introduction | https://github.com/COS420-F25/F26-Group-A/issues/30 | Done | Low | Requirements | 2 |  | Elorm-K |  | Kelvin N. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 1 QC
Write Overall Description | https://github.com/COS420-F25/F26-Group-A/issues/28 | Done | Low | Requirements | 2 |  | Elorm-K |  | Ryan B. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 1 QC
Cyril to add his Screenshot to README | https://github.com/COS420-F25/F26-Group-A/issues/64 | Done | Low |  |  |  | Elorm-K |  | Andrew B. | 2026-10-20 | 2026-10-23 | D2
Line-by-line rubric QC of the whole deliverable | https://github.com/COS420-F25/F26-Group-A/issues/59 | Quality Checking | Low | Technical work | 4 |  | winslop11 |  | Cyril A. | 2026-10-25 | 2026-10-26 | D2 | Deliverable 2 Submission
Export Product Backlog | https://github.com/COS420-F25/F26-Group-A/issues/46 | Quality Checking | Low | Requirements | 1 |  | Apex-04 |  | Cyril A. |  | 2026-10-23 | D2 | Deliverable 2 QC
Update Wiki with QC Procedure | https://github.com/COS420-F25/F26-Group-A/issues/42 | Done |  |  |  |  | zen2504 |  | Cyril A. |  |  | D2