## F26 TeamA Project - Sprint Back
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint | Milestone
Turn D1 comments from Greg and turn Brightspace feedback to tasks | https://github.com/COS420-F25/F26-Group-A/issues/43 | Todo / Sprint Backlog | High | Requirements | 3 | 1 | Elorm-K |  | Kelvin N. | 2026-10-19 | 2026-10-20 | D2 | Deliverable 1 Corrections
Write Issue Process in Wiki | https://github.com/COS420-F25/F26-Group-A/issues/40 | Done | High | Knowledge acquisition | 2 | 2 | Apex-04 |  | Cyril A. | 2026-10-18 | 2026-10-19 | D2
Export Sprint Backlog 1 (Post-Kickoff) | https://github.com/COS420-F25/F26-Group-A/issues/44 | Todo / Sprint Backlog | High | Requirements | 1 |  | Apex-04 |  | Cyril A. | 2026-10-19 | 2026-10-20 | D2 | Deliverable 2 QC
Revise product backlog, reply to D1 comments | https://github.com/COS420-F25/F26-Group-A/issues/45 | Todo / Sprint Backlog | High | Technical work | 1 |  | ngkelvn |  | Andrew B. |  | 2026-10-21 | D2 | Deliverable 1 Corrections
Export Product Backlog | https://github.com/COS420-F25/F26-Group-A/issues/46 | Todo / Sprint Backlog | High | Requirements | 1 |  | Apex-04 |  | Cyril A. |  | 2026-10-23 | D2 | Deliverable 2 QC
UML Package Diagram | https://github.com/COS420-F25/F26-Group-A/issues/47 | Todo / Sprint Backlog | High | Requirements | 3 |  | Apex-04 |  | Ryan B. |  | 2026-10-22 | D2 | Deliverable 2 QC
2 Mockups, Improve D1 wireframes, place in SRS | https://github.com/COS420-F25/F26-Group-A/issues/49 | Todo / Sprint Backlog | High | Requirements | 2 |  | ryanhallett |  | Cyril A. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 2 QC
Set Up Build Enviroment and Dependecies | https://github.com/COS420-F25/F26-Group-A/issues/54 | Todo / Sprint Backlog | High | Technical work | 2 | 1 | Apex-04 |  | Ryan H. | 2026-10-19 | 2026-10-21 | D2 | Deliverable 2 QC
Merge A2 diagrams | https://github.com/COS420-F25/F26-Group-A/issues/51 | Todo / Sprint Backlog | High | Requirements | 3 |  | ryanhallett |  | Cyril A. | 2026-10-20 | 2026-10-20 | D2 | Deliverable 2 Submission
Update Readme with Explicit Download and Installation Instuctions | https://github.com/COS420-F25/F26-Group-A/issues/57 | Todo / Sprint Backlog | High | Requirements | 1 |  | ryanhallett |  | Andrew B. |  | 2026-10-22 | D2 | Deliverable 2 QC
Integrate all D2 docs, links, submission folder | https://github.com/COS420-F25/F26-Group-A/issues/58 | Todo / Sprint Backlog | High | Requirements | 2 |  | Elorm-K, winslop11 |  | Andrew B. | 2026-10-25 | 2026-10-26 | D2 | Deliverable 2 QC
Update the wireframes using already existing example | https://github.com/COS420-F25/F26-Group-A/issues/63 | Todo / Sprint Backlog | High | Requirements | 4 |  | alexh5427, Elorm-K, ryanhallett |  | Andrew B. | 2026-10-20 | 2026-10-23 | D2 | Deliverable 2 QC
Respond to feedback on functional requirements that need editing | https://github.com/COS420-F25/F26-Group-A/issues/62 | Todo / Sprint Backlog | Medium | Requirements | 1 |  | zen2504 |  | Ryan H. | 2026-10-20 | 2026-10-23 | D2
2 Mockups, Improve D1 wireframes, place in SRS | https://github.com/COS420-F25/F26-Group-A/issues/52 | Todo / Sprint Backlog | Medium | Requirements | 2 |  | alexh5427 |  | Zach B. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 2 QC
Write SRS introduction | https://github.com/COS420-F25/F26-Group-A/issues/30 | Product Backlog | Low | Requirements | 2 |  | Apex-04 |  | Kelvin N. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 1 QC
Write Overall Description | https://github.com/COS420-F25/F26-Group-A/issues/28 | Product Backlog | Low | Requirements | 2 |  | Elorm-K |  | Ryan B. | 2026-10-19 | 2026-10-23 | D2 | Deliverable 1 QC
Line-by-line rubric QC of the whole deliverable | https://github.com/COS420-F25/F26-Group-A/issues/59 | Todo / Sprint Backlog | Low | Technical work | 4 |  | winslop11 |  | Cyril A. | 2026-10-25 | 2026-10-26 | D2 | Deliverable 2 Submission
Export Sprint Backlog 2 | https://github.com/COS420-F25/F26-Group-A/issues/60 | Todo / Sprint Backlog | Low | Technical work | 1 |  | Apex-04 |  | Cyril A. |  | 2026-10-25 | D2 | Deliverable 2 QC